## Sheet1
#### **Feature 1.2: Set Up API Service**
- **Task**: Set up the API service to interact with the Event Service.
- **Action**:
- Create an `eventService.js` file to handle API calls related to lesson scheduling.
- Implement functions for creating, updating, fetching, and deleting lessons.
- **Deliverable**: API service functions for lesson scheduling.
Objective 1.3: Create Basic Components
Task: Create basic React components for lesson scheduling.
Action:
LessonCalendar.jsx: Component to display the calendar view and handle interactions.
requirements:
individual date grids can show first two lessons scheduled on that date (sorted by time) in the main view, if more than three lessons display up/down arrows to indicate overflow.
clicking on an existing lesson should bring up LessonModal.jsx component
update Calendar State when events are created/deleted
LessonModal.jsx: Component to display a modal for viewing, creating, and editing lessons.
LesonModal will have 2 States
State #1:
LessonList.jsx
State #2:
LessonForm.jsx
Use Case: User clicks an individual lesson => should bring up LessonModal populated with the lesson event data (form will be in edit lesson state)
LessonForm.jsx: Component for simpler formbased view to create and edit lessons.
LessonForm component can have 2 states if needed, one for the modal view and 1 for the Schedule page view
LessonList.jsx: Component to display a list of lessons.
LessonList component can have 2 states if needed, one for the modal view and 1 for the Schedule page view
Deliverable: Basic UI components
Objective 2.1: Integrate Calendar View and Modal
Task: Integrate the LessonCalendar component with the LessonModal component and the API.
Action:
Use Fullcalendar calendar library for the LessonCalendar component.
Implement click handlers to open the LessonModal with appropriate data.
Connect LessonModal to API functions for creating, updating, and deleting lessons.
Deliverable: Functional LessonCalendar and LessonModal components.
Objective 2.2: Integrate Form and List View
Task: Integrate the LessonForm and LessonList components with the API.
Action:
Connect LessonForm to the createLesson and editLesson API functions.
Connect LessonList to the fetchLessons and deleteLesson API functions.
Deliverable: Functional LessonForm and LessonList components.
Use Case:
user clicks on a single lesson in calendar
Expected Behavior:
render LessonForm in read only mode
form has appropriate buttons to edit or delete the lesson